## Sheet1
Sprint | Description | Role | Need | Requirement | Priority | Estimate | Time | Status
1 | Server & Account Have a basic frame that helps restaurant manager can sign in, manage informations about his restaurant | Server manager | Active server | Server can work | 1 | Must |  | using localhost instead
|  | Restaurant Manager | Database form | Design menu Required functions: - Add lists of dish - Add dish (need to have ID, images, description, cost, status (new or old) - Edit dish - Remove dish - Allow to customize arrangement | 2 | Must |  | checking
|  |  |  | Create a table that stores lists of using tables in the restaurant Can update the status (using or free) | 2 | Must |  | checking
|  | Server manager | Database that stores lists of accounts | Accounts decentralization: customer and restaurant manager | 3 | Should |  | checking
2 | Sign in & Sign up | Client | Sign in form | Sign in with Google +, Facebook, ... | 2 |  |  | checking
|  | Server | Sign in | Provide a private account for restaurant manager | 1 |  |  | checking
|  |  | Sign up | Not free, need to active | 1 | Must |  | not done
3 | Restaurant | Restaurant Manager (On server) | Receive order from customer (Client) |  | 1 | Must |  | not done
|  | Customer (Client) | Display lists of available restaurants on server | Can select an arbitrariness restaurant | 1 | Must |  | not done
4 | Order Use to order dish and send request to the restaurant (Client) | Customer (At home) | Display lists of available dish in the restaurant | - New dish should be placed on top of list | 1 | Must |  | not done
|  |  |  | - Display fully informations about name, cost, illustrative images and detail about dish (if available) |  |  |  | image
|  |  |  | - Display number of free tables at the chosen time |  |  |  | not done
|  |  | Display temporary customers' order to see what they chose | - Add, subtract number of dish | 1 | Must |  | done
- Delete dish
- Calculate money automatically
- Allow to choose time and table before
|  |  |  | - Reset order | 3 | Should |  | done
|  |  | Confirm that order has sent | - Send data to restaurant's server | 2 | Must |  | not done
|  |  |  | - Print bills | 3 |  |  | not done
|  |  |  | - Save order in customers' history | 3 | Should |  | not done
|  |  | Display order's history of customers |  | 4 |  |  | not done
5 | Menu | Customer (Client) | Show menu of the selected restaurant | Display all infomations about all dishes in the menu | 1 | Must |  | not done
|  |  |  | Display statuses of all dishes which include attribute new | 2 | Should |  | not done
6 | Customer information | Customer |  | Be able to modify customer information | 2 | Must
|  |  |  | Show all information about customer | 1 | Must